
[image: ]                                                    
                                                                                                                                          
  	
                                                                                                                                                                 
                                                                                                                                                                                      P.O. BOX 10337  GOLDSBORO, N.C. 27532   
                                                                                                                                                                                              PHONE 919-778-4525

[image: ]                                                    
                                                                                                                                          
  	
                                                                                                                                                                 
                                                                                                                                                                                      P.O. BOX 10337  GOLDSBORO, N.C. 27532   
                                                                                                                                                                                              PHONE 919-778-4525
BID PACKAGE BP-01 – SELECTIVE DEMOLITION
Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425
Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)
Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525
	1. SUMMARY AND KEY DATES



Interior selective demolition of Food Lab 100 per AD-101A, including MEP demolition, slab removal for underground utilities, and storefront opening preparation. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.
	Pre-bid meeting
	Mon 10/12, 2:00 PM, Pender HS front office
	Prequalification due
	Wed 10/14, 5:00 PM

	RFIs due
	Wed 10/14, 5:00 PM, estimating@danddcc.com
	Prequalified list / protests
	Thu 10/15 / noon Fri 10/16

	Final addendum
	Thu 10/15
	Bid opening
	Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw

	Notice to Proceed
	11/3/2026 (anticipated)
	Substantial / Final
	Jan 4 / Jan 15, 2027 (confirm by addendum)


 
	2. SCOPE OF WORK (furnish and install complete, including but not limited to)



· All demolition per AD-101A keynotes: VCT and bulk adhesive, CMU and metal stud walls, doors and frames, casework and countertops, toilet accessories, ACT ceilings and grid, abandoned anchors and fasteners. Salvage items to Owner where noted (including the fire extinguisher cabinet).
· GPR scan, then saw-cut and remove the slab in the hatched area (about 790 SF) with clean, straight cuts for S2 dowels. Wet or HEPA-shrouded cutting; slurry vacuumed and removed.
· Remove the exterior door/frame for storefront S2 and the abandoned vent and fan sleeves. Provide and maintain secure, weathertight temporary infill until the permanent work is installed.
· Protect all finishes, walks and work to remain.
· MEP demolition per PD-101, M-101 and E-101 after BP-10, BP-11 and BP-12 have disconnected, capped and made safe: plumbing fixtures, water heater, piping, ductwork, air devices, the sidewall exhaust fan, lights, conduit, plug-mold and devices. Do not remove anything not tagged safe by the MEP trade. Turn salvage items over to the Owner (WAPs, projector, track lights).
· Furnish and pay for its own dumpsters, pulls and disposal for all demolition debris. Remove dumpsters and restore the area when complete.
· Daily cleanup of demolition areas and a final broom-clean at completion of demolition, ready for following trades.
· Demolition plan submittal and a pre-demolition photo/video survey with the CM.
References: Specs 024100, 013516, 015000. Drawings AD-101A, S2, P-401, E-102. All other sections and sheets as they apply.
 
	3. WORK BY OTHERS AND CLARIFICATIONS



Not included: MEP disconnects, capping and make-safe, and removal of fire alarm devices and exit signs to be reinstalled (BP-10, BP-11, BP-12); Excavation and backfill (BP-10, BP-12) and pour-back (BP-02); Masonry and GWB patching (BP-03, BP-05); Final floor grinding (BP-07); Hazardous material abatement (Owner); Lockers (relocated by BP-14).
· Price full removal of the hatched slab area; give a deduct for 2'-0" trench-only removal below.
· No hazmat survey is provided. VCT and mastic are assumed non-asbestos; stop and notify the CM if suspect material is found.
 
	4. GENERAL REQUIREMENTS



· Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.
· Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.
· Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.
· School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).
· Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.
· Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

	BID FORM – BP-01 SELECTIVE DEMOLITION



The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-01 – Selective Demolition, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:
	Company
	
	NC License No. / Class
	

	Address
	
	Contact / Phone
	

	Email
	
	Prequalified? (Y/N)
	


A. Base Bid (lump sum, 100% turnkey)
	Written in words
	

	Figures
	$


B. Requested Pricing
	Description
	Amount

	Deduct for trench-only slab removal (2'-0" wide) in lieu of full hatched area
	Deduct $


C. Unit Prices (installed, including overhead and profit)
	Description
	Unit
	Unit Price

	Additional slab saw-cut and removal
	SF
	$

	Additional CMU wall removal
	SF
	$


D. Lead Times and Duration
	Item
	Weeks / days
	Notes

	Submittals after award (working days)
	
	

	Material lead time (weeks)
	
	

	On-site duration (working days) / crew size
	
	


E. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)
	


F. Addenda Received
	No.
	
	No.
	
	No.
	
	No.
	


Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).
	Authorized Signature
	
	Date
	

	Name / Title
	
	Federal TIN
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