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BID PACKAGE BP-04 – ALUMINUM STOREFRONT, GLAZING & DOOR HARDWARE
Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425
Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)
Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525
	1. SUMMARY AND KEY DATES



Storefronts S1 and S2, entrance pair Door 100A, glazing, insulated panels, and door hardware. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.
	Pre-bid meeting
	Mon 10/12, 2:00 PM, Pender HS front office
	Prequalification due
	Wed 10/14, 5:00 PM

	RFIs due
	Wed 10/14, 5:00 PM, estimating@danddcc.com
	Prequalified list / protests
	Thu 10/15 / noon Fri 10/16

	Final addendum
	Thu 10/15
	Bid opening
	Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw

	Notice to Proceed
	11/3/2026 (anticipated)
	Substantial / Final
	Jan 4 / Jan 15, 2027 (confirm by addendum)


 
	2. SCOPE OF WORK (furnish and install complete, including but not limited to)



· Thermally broken storefront S1 and S2 per A-601, with delegated wind-load design, anchorage, sill flashing with end dams, and perimeter sealant.
· Door 100A: pair of medium-stile thermal entrance doors with removable keyed mullion.
· Tempered insulating glass (SNX 60+) and Mapes insulated infill panels, with a framed opening in S1 for the DOAS duct.
· Complete door hardware for 100A (see clarification), with construction and permanent cores keyed to the Owner's system and attendance at the keying meeting.
· AAMA 501.2 field water testing (two tests minimum) with repair and retest, protection, final cleaning of glass and frames, and warranties (10 years on IG units).
· BEST full-size interchangeable cores per 087100 (verify against the Owner's keying standard), including spare cylinders as specified.
References: Specs 084313, 087100, 080671, 088000. Drawings A-601, A-101A, M-101. All other sections and sheets as they apply.
 
	3. WORK BY OTHERS AND CLARIFICATIONS



Not included: Opening prep and temporary infill (BP-01); Masonry jambs (BP-03); Duct sleeve and seal at S1 (BP-11); Electrified hardware or access control (not shown).
· Hardware Set #1 is blank. Price: continuous hinges, rim exit devices with cylinder dogging, lever trim, keyed removable mullion, closers, SFIC cores, threshold, weatherstripping, sweeps, stops and kick plates.
· The door schedule width conflicts with the S2 elevation; price per the elevation and field verify.
· Section 084313 lists both organic coating and clear anodized finish. Price Class I clear anodized, and give the add or deduct for 70% PVDF (Kynar) below.
 
	4. GENERAL REQUIREMENTS



· Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.
· Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.
· Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.
· School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).
· Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.
· Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

	BID FORM – BP-04 ALUMINUM STOREFRONT, GLAZING & DOOR HARDWARE



The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-04 – Aluminum Storefront, Glazing & Door Hardware, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:
	Company
	
	NC License No. / Class
	

	Address
	
	Contact / Phone
	

	Email
	
	Prequalified? (Y/N)
	


A. Base Bid (lump sum, 100% turnkey)
	Written in words
	

	Figures
	$


B. Requested Pricing
	Description
	Amount

	Value of door hardware included in Base Bid
	$

	Add / (deduct) for 70% PVDF (Kynar) finish in lieu of clear anodized
	$


C. Unit Prices (installed, including overhead and profit)
	Description
	Unit
	Unit Price

	Additional storefront with IG
	SF
	$

	Additional insulated infill panel
	SF
	$


D. Lead Times and Duration
	Item
	Weeks / days
	Notes

	Submittals after award (working days)
	
	

	Material lead time (weeks)
	
	

	On-site duration (working days) / crew size
	
	


E. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)
	


F. Addenda Received
	No.
	
	No.
	
	No.
	
	No.
	


Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).
	Authorized Signature
	
	Date
	

	Name / Title
	
	Federal TIN
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