BID PACKAGE BP-05 – METAL STUDS, DRYWALL, ACOUSTICAL CEILINGS & ROUGH CARPENTRY

Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425

Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)

Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525

1. SUMMARY AND KEY DATES

Temporary partitions, metal framing, gypsum board, blocking, and ACT ceilings. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.

| Pre-bid meeting | Mon 10/12, 2:00 PM, Pender HS front office | Prequalification due | Wed 10/14, 5:00 PM |
| --- | --- | --- | --- |
| RFIs due | Wed 10/14, 5:00 PM, estimating@danddcc.com | Prequalified list / protests | Thu 10/15 / noon Fri 10/16 |
| Final addendum | Thu 10/15 | Bid opening | Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw |
| Notice to Proceed | 11/3/2026 (anticipated) | Substantial / Final | Jan 4 / Jan 15, 2027 (confirm by addendum) |

2. SCOPE OF WORK (furnish and install complete, including but not limited to)

- Temporary full-height dust partitions with lockable gasketed doors, relocated as needed and removed at completion (price about 40 LF, two doors, one relocation).

- Partitions, furring, soffits and GWB ceilings per A-005, A-101A and A-701, including deflection track, Level 4/5 finish and the ACT-to-GWB transition.

- Island knee walls with 6" studs and 5/8" sheathing to receive PLAM panels, framed around the steel posts.

- Patch all GWB walls and ceilings disturbed by demolition and MEP work, ready for paint.

- FRT blocking for all wall-mounted items by all trades (casework, shelves, TVs, hooks, lockers, FEC, accessories, equipment), located from approved shop drawings.

- Install access panels furnished by MEP trades.

- ACT-1 ceilings on intermediate-duty grid with seismic bracing as required, plus 5% attic stock.

- Acoustic insulation and acoustical sealant per partition types; framing, insulation and GWB infill at walls and doors removed by demolition.

- Rough openings for the semi-recessed FEC12 and other recessed items.

- Alternates: Alt 2 – West wall casework – blocking; Alt 6 – Floating shelves – blocking; Alt 7 – Demonstration station – framing and blocking.

References: Specs 015000, 061053, 092116, 095100. Drawings A-005, A-101A, A-701, A-721. All other sections and sheets as they apply.

3. WORK BY OTHERS AND CLARIFICATIONS

Not included: Steel posts (BP-13); PLAM panels (BP-06); Painting (BP-08); Fixture and diffuser support wires (installing trade).

- Untagged walls: match the nearest tagged partition type.

- ACT seismic category is unclear; state the category assumed.

4. GENERAL REQUIREMENTS

- Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.

- Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.

- Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.

- School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).

- Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.

- Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

BID FORM – BP-05 METAL STUDS, DRYWALL, ACOUSTICAL CEILINGS & ROUGH CARPENTRY

The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-05 – Metal Studs, Drywall, Acoustical Ceilings & Rough Carpentry, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:

| Company |  | NC License No. / Class |  |
| --- | --- | --- | --- |
| Address |  | Contact / Phone |  |
| Email |  | Prequalified? (Y/N) |  |

A. Base Bid (lump sum, 100% turnkey)

| Written in words |  |
| --- | --- |
| Figures | $ |

B. Alternates (ADD or DEDUCT; write “No Change” if none)

| No. | Description | Amount |
| --- | --- | --- |
| Alt 2 | West wall casework – blocking | Add / Deduct $ |
| Alt 6 | Floating shelves – blocking | Add / Deduct $ |
| Alt 7 | Demonstration station – framing and blocking | Add / Deduct $ |

C. Unit Prices (installed, including overhead and profit)

| Description | Unit | Unit Price |
| --- | --- | --- |
| Metal stud partition, GWB both sides, to 12' | LF | $ |
| GWB patch, ready for paint | SF | $ |
| ACT-1 with grid | SF | $ |
| Additional temporary dust partition | LF | $ |

D. Lead Times and Duration

| Item | Weeks / days | Notes |
| --- | --- | --- |
| Submittals after award (working days) |  |  |
| Material lead time (weeks) |  |  |
| On-site duration (working days) / crew size |  |  |

E. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)

F. Addenda Received

| No. |  | No. |  | No. |  | No. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).

| Authorized Signature |  | Date |  |
| --- | --- | --- | --- |
| Name / Title |  | Federal TIN |  |