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BID PACKAGE BP-05 – METAL STUDS, DRYWALL, ACOUSTICAL CEILINGS & ROUGH CARPENTRY
Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425
Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)
Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525
	1. SUMMARY AND KEY DATES



Temporary partitions, metal framing, gypsum board, blocking, and ACT ceilings. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.
	Pre-bid meeting
	Mon 10/12, 2:00 PM, Pender HS front office
	Prequalification due
	Wed 10/14, 5:00 PM

	RFIs due
	Wed 10/14, 5:00 PM, estimating@danddcc.com
	Prequalified list / protests
	Thu 10/15 / noon Fri 10/16

	Final addendum
	Thu 10/15
	Bid opening
	Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw

	Notice to Proceed
	11/3/2026 (anticipated)
	Substantial / Final
	Jan 4 / Jan 15, 2027 (confirm by addendum)


 
	2. SCOPE OF WORK (furnish and install complete, including but not limited to)



· Temporary full-height dust partitions with lockable gasketed doors, relocated as needed and removed at completion (price about 40 LF, two doors, one relocation).
· Partitions, furring, soffits and GWB ceilings per A-005, A-101A and A-701, including deflection track, Level 4/5 finish and the ACT-to-GWB transition.
· Island knee walls with 6" studs and 5/8" sheathing to receive PLAM panels, framed around the steel posts.
· Patch all GWB walls and ceilings disturbed by demolition and MEP work, ready for paint.
· FRT blocking for all wall-mounted items by all trades (casework, shelves, TVs, hooks, lockers, FEC, accessories, equipment), located from approved shop drawings.
· Install access panels furnished by MEP trades.
· ACT-1 ceilings on intermediate-duty grid with seismic bracing as required, plus 5% attic stock.
· Acoustic insulation and acoustical sealant per partition types; framing, insulation and GWB infill at walls and doors removed by demolition.
· Rough openings for the semi-recessed FEC12 and other recessed items.
· Alternates: Alt 2 – West wall casework – blocking; Alt 6 – Floating shelves – blocking; Alt 7 – Demonstration station – framing and blocking.
References: Specs 015000, 061053, 092116, 095100. Drawings A-005, A-101A, A-701, A-721. All other sections and sheets as they apply.
 
	3. WORK BY OTHERS AND CLARIFICATIONS



Not included: Steel posts (BP-13); PLAM panels (BP-06); Painting (BP-08); Fixture and diffuser support wires (installing trade).
· Untagged walls: match the nearest tagged partition type.
· ACT seismic category is unclear; state the category assumed.
 
	4. GENERAL REQUIREMENTS



· Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.
· Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.
· Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.
· School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).
· Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.
· Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

	BID FORM – BP-05 METAL STUDS, DRYWALL, ACOUSTICAL CEILINGS & ROUGH CARPENTRY



The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-05 – Metal Studs, Drywall, Acoustical Ceilings & Rough Carpentry, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:
	Company
	
	NC License No. / Class
	

	Address
	
	Contact / Phone
	

	Email
	
	Prequalified? (Y/N)
	


A. Base Bid (lump sum, 100% turnkey)
	Written in words
	

	Figures
	$


B. Alternates (ADD or DEDUCT; write “No Change” if none)
	No.
	Description
	Amount

	Alt 2
	West wall casework – blocking
	Add / Deduct $

	Alt 6
	Floating shelves – blocking
	Add / Deduct $

	Alt 7
	Demonstration station – framing and blocking
	Add / Deduct $


C. Unit Prices (installed, including overhead and profit)
	Description
	Unit
	Unit Price

	Metal stud partition, GWB both sides, to 12'
	LF
	$

	GWB patch, ready for paint
	SF
	$

	ACT-1 with grid
	SF
	$

	Additional temporary dust partition
	LF
	$


D. Lead Times and Duration
	Item
	Weeks / days
	Notes

	Submittals after award (working days)
	
	

	Material lead time (weeks)
	
	

	On-site duration (working days) / crew size
	
	


E. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)
	


F. Addenda Received
	No.
	
	No.
	
	No.
	
	No.
	


Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).
	Authorized Signature
	
	Date
	

	Name / Title
	
	Federal TIN
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