BID PACKAGE BP-07 – FLOORING

Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425

Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)

Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525

1. SUMMARY AND KEY DATES

Moisture testing, floor preparation, terrazzo wall base, and Alternate 4 resinous flooring. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.

| Pre-bid meeting | Mon 10/12, 2:00 PM, Pender HS front office | Prequalification due | Wed 10/14, 5:00 PM |
| --- | --- | --- | --- |
| RFIs due | Wed 10/14, 5:00 PM, estimating@danddcc.com | Prequalified list / protests | Thu 10/15 / noon Fri 10/16 |
| Final addendum | Thu 10/15 | Bid opening | Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw |
| Notice to Proceed | 11/3/2026 (anticipated) | Substantial / Final | Jan 4 / Jan 15, 2027 (confirm by addendum) |

2. SCOPE OF WORK (furnish and install complete, including but not limited to)

- Engage and pay an independent agency for moisture (RH) and pH testing per 090561.

- Final floor prep after VCT removal: grind to the profile required by the finish, remove remaining adhesive, repair cracks and joints, skim coat, and blend at pour-backs.

- CB-1 precast epoxy terrazzo coved base with cap strips, scribed at doors and casework.

- Transitions at doors, sequencing with the CM, and protection.

- Alternates: Alt 4 – EPF-1 resinous flake flooring per 096700 (gross add).

References: Specs 090561, 096623, 096700. Drawings A-101A, A-651, A-801A. All other sections and sheets as they apply.

3. WORK BY OTHERS AND CLARIFICATIONS

Not included: VCT and bulk adhesive removal (BP-01); Pour-backs (BP-02); Sealed concrete SCT-1 (BP-08); Moisture mitigation (unit price).

- A-651 lists CB-1 as both terrazzo and vinyl base. Price terrazzo, and give a deduct for 4" vinyl below.

4. GENERAL REQUIREMENTS

- Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.

- Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.

- Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.

- School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).

- Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.

- Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

BID FORM – BP-07 FLOORING

The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-07 – Flooring, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:

| Company |  | NC License No. / Class |  |
| --- | --- | --- | --- |
| Address |  | Contact / Phone |  |
| Email |  | Prequalified? (Y/N) |  |

A. Base Bid (lump sum, 100% turnkey)

| Written in words |  |
| --- | --- |
| Figures | $ |

B. Alternates (ADD or DEDUCT; write “No Change” if none)

| No. | Description | Amount |
| --- | --- | --- |
| Alt 4 | EPF-1 resinous flake flooring per 096700 (gross add) | Add / Deduct $ |

C. Requested Pricing

| Description | Amount |
| --- | --- |
| Deduct for 4" vinyl base in lieu of terrazzo base | Deduct $ |

D. Unit Prices (installed, including overhead and profit)

| Description | Unit | Unit Price |
| --- | --- | --- |
| Moisture mitigation system | SF | $ |
| Self-leveler, per 1/8" | SF | $ |
| Crack / joint repair | LF | $ |

E. Lead Times and Duration

| Item | Weeks / days | Notes |
| --- | --- | --- |
| Submittals after award (working days) |  |  |
| Material lead time (weeks) |  |  |
| On-site duration (working days) / crew size |  |  |

F. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)

G. Addenda Received

| No. |  | No. |  | No. |  | No. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).

| Authorized Signature |  | Date |  |
| --- | --- | --- | --- |
| Name / Title |  | Federal TIN |  |