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BID PACKAGE BP-08 – PAINTING, SEALED CONCRETE & WALL GRAPHICS
Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425
Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)
Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525
	1. SUMMARY AND KEY DATES



Interior painting, sealed concrete floor (SCT-1), and Alternate 1 wall graphics. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.
	Pre-bid meeting
	Mon 10/12, 2:00 PM, Pender HS front office
	Prequalification due
	Wed 10/14, 5:00 PM

	RFIs due
	Wed 10/14, 5:00 PM, estimating@danddcc.com
	Prequalified list / protests
	Thu 10/15 / noon Fri 10/16

	Final addendum
	Thu 10/15
	Bid opening
	Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw

	Notice to Proceed
	11/3/2026 (anticipated)
	Substantial / Final
	Jan 4 / Jan 15, 2027 (confirm by addendum)


 
	2. SCOPE OF WORK (furnish and install complete, including but not limited to)



· Paint all new and existing walls, ceilings, soffits and doors/frames in finished areas per A-651 and the A-701 color blocking (field colors and accent blocks).
· Paint exposed piping, conduit, duct and steel in finished areas. Caulk, patch and touch up after other trades; lead-safe (RRP) practices on existing painted surfaces.
· SCT-1 sealed concrete with slip-resistant additive (paint system I-TR-C), applied after prep by BP-07 and before casework is set.
· One gallon of each color as attic stock.
· Alternates: Alt 1 – Experiential wall graphics, including design services; Alt 4 – Deduct SCT-1 if resinous flooring is accepted.
References: Specs 099123, 097200. Drawings A-651, A-701, A-801A, A-101A. All other sections and sheets as they apply.
 
	3. WORK BY OTHERS AND CLARIFICATIONS



Not included: Floor grinding and testing (BP-07); Shop priming (BP-13); Factory-finished items.
· Per Section 012300, all graphics (FOOD LAB, Vision–Mission–Values and "Painted Graphic TBD" areas), including design, production and installation, are Alternate 1. The Base Bid is field colors and accent blocks only.
 
	4. GENERAL REQUIREMENTS



· Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.
· Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.
· Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.
· School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).
· Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.
· Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

	BID FORM – BP-08 PAINTING, SEALED CONCRETE & WALL GRAPHICS



The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-08 – Painting, Sealed Concrete & Wall Graphics, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:
	Company
	
	NC License No. / Class
	

	Address
	
	Contact / Phone
	

	Email
	
	Prequalified? (Y/N)
	


A. Base Bid (lump sum, 100% turnkey)
	Written in words
	

	Figures
	$


B. Alternates (ADD or DEDUCT; write “No Change” if none)
	No.
	Description
	Amount

	Alt 1
	Experiential wall graphics, including design services
	Add / Deduct $

	Alt 4
	Deduct SCT-1 if resinous flooring is accepted
	Add / Deduct $


C. Requested Pricing
	Description
	Amount

	Alt 1 breakdown – graphic design services portion (included in Alt 1)
	$


D. Unit Prices (installed, including overhead and profit)
	Description
	Unit
	Unit Price

	Wall paint, two coats over primer
	SF
	$

	Sealed concrete SCT-1
	SF
	$


E. Lead Times and Duration
	Item
	Weeks / days
	Notes

	Submittals after award (working days)
	
	

	Material lead time (weeks)
	
	

	On-site duration (working days) / crew size
	
	


F. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)
	


G. Addenda Received
	No.
	
	No.
	
	No.
	
	No.
	


Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).
	Authorized Signature
	
	Date
	

	Name / Title
	
	Federal TIN
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