BID PACKAGE BP-10 – PLUMBING

Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425

Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)

Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525

1. SUMMARY AND KEY DATES

Make-safe for demolition, waste/vent, domestic water, propane gas, fixtures, water heater, and equipment connections. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.

| Pre-bid meeting | Mon 10/12, 2:00 PM, Pender HS front office | Prequalification due | Wed 10/14, 5:00 PM |
| --- | --- | --- | --- |
| RFIs due | Wed 10/14, 5:00 PM, estimating@danddcc.com | Prequalified list / protests | Thu 10/15 / noon Fri 10/16 |
| Final addendum | Thu 10/15 | Bid opening | Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw |
| Notice to Proceed | 11/3/2026 (anticipated) | Substantial / Final | Jan 4 / Jan 15, 2027 (confirm by addendum) |

2. SCOPE OF WORK (furnish and install complete, including but not limited to)

- Coordinate plumbing demolition with BP-01: shut off, drain, disconnect and cap all piping and fixtures shown on PD-101 at mains or below grade, and mark items safe for removal. BP-01 removes and disposes.

- Mark trench routes for saw-cutting, then excavate, bed, install, test and backfill all underground waste and vent. Camera-inspect the existing drain before tie-in.

- Domestic hot, cold and return water with a new main shutoff valve and mixing valves. Flush, disinfect and test.

- Propane piping from the Owner's tank/first-stage regulator (2 psi) to the appliances and water heater: underground PE with tracer wire, regulators, shutoffs, gas solenoid valve and the encasement vent. Install LP conversion kits on the Owner's ranges; test, purge and obtain inspection.

- Fixtures (SK-1, SK-2, SK-3, FD-1, FS-1) with trim. WH-1 propane water heater with pad, venting and expansion tank; CP-1 circulator.

- Connections to dishwashers, ice maker and hoods; DOAS condensate to the existing catch basin, including exterior trench and restoration.

- Permits, coordination, access panels furnished, firestopping, as-builts and O&M.

- Include 10 CY of rock excavation per Section 220100.

- Alternates: Alt 3 – South wall sink and plumbing finish; Alt 7 – Demonstration station plumbing and gas finish.

References: Division 22. Drawings PD-101, P-001, P-101, P-401, P-402, A-911A. All other sections and sheets as they apply.

3. WORK BY OTHERS AND CLARIFICATIONS

Not included: Removal and disposal of demolished plumbing (BP-01); Slab cutting (BP-01) and pour-back (BP-02); Propane tank and first-stage regulator (Owner/supplier); Power wiring (BP-12); Roof flashing (BP-09).

- The propane tank location is not shown. Price up to 175 LF developed length from the tank and state the length assumed.

- Alts 3 and 7: rough-in is in the Base Bid; the alternates are finish only.

4. GENERAL REQUIREMENTS

- Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.

- Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.

- Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.

- School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).

- Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.

- Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

BID FORM – BP-10 PLUMBING

The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-10 – Plumbing, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:

| Company |  | NC License No. / Class |  |
| --- | --- | --- | --- |
| Address |  | Contact / Phone |  |
| Email |  | Prequalified? (Y/N) |  |

A. Base Bid (lump sum, 100% turnkey)

| Written in words |  |
| --- | --- |
| Figures | $ |

B. Alternates (ADD or DEDUCT; write “No Change” if none)

| No. | Description | Amount |
| --- | --- | --- |
| Alt 3 | South wall sink and plumbing finish | Add / Deduct $ |
| Alt 7 | Demonstration station plumbing and gas finish | Add / Deduct $ |

C. Requested Pricing

| Description | Amount |
| --- | --- |
| Add for new propane tank and first-stage regulator through the gas supplier | Add $ |

D. Unit Prices (installed, including overhead and profit)

| Description | Unit | Unit Price |
| --- | --- | --- |
| Underground 4" waste incl. excavation | LF | $ |
| 1" propane piping | LF | $ |
| Additional floor drain | EA | $ |
| Rock excavation beyond 10 CY | CY | $ |
| Replace deteriorated existing cast-iron waste, 4" | LF | $ |

E. Lead Times and Duration

| Item | Weeks / days | Notes |
| --- | --- | --- |
| Submittals after award (working days) |  |  |
| Material lead time (weeks) |  |  |
| On-site duration (working days) / crew size |  |  |

F. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)

G. Addenda Received

| No. |  | No. |  | No. |  | No. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).

| Authorized Signature |  | Date |  |
| --- | --- | --- | --- |
| Name / Title |  | Federal TIN |  |