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BID PACKAGE BP-10 – PLUMBING
Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425
Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)
Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525
	1. SUMMARY AND KEY DATES



Make-safe for demolition, waste/vent, domestic water, propane gas, fixtures, water heater, and equipment connections. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.
	Pre-bid meeting
	Mon 10/12, 2:00 PM, Pender HS front office
	Prequalification due
	Wed 10/14, 5:00 PM

	RFIs due
	Wed 10/14, 5:00 PM, estimating@danddcc.com
	Prequalified list / protests
	Thu 10/15 / noon Fri 10/16

	Final addendum
	Thu 10/15
	Bid opening
	Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw

	Notice to Proceed
	11/3/2026 (anticipated)
	Substantial / Final
	Jan 4 / Jan 15, 2027 (confirm by addendum)


 
	2. SCOPE OF WORK (furnish and install complete, including but not limited to)



· Coordinate plumbing demolition with BP-01: shut off, drain, disconnect and cap all piping and fixtures shown on PD-101 at mains or below grade, and mark items safe for removal. BP-01 removes and disposes.
· Mark trench routes for saw-cutting, then excavate, bed, install, test and backfill all underground waste and vent. Camera-inspect the existing drain before tie-in.
· Domestic hot, cold and return water with a new main shutoff valve and mixing valves. Flush, disinfect and test.
· Propane piping from the Owner's tank/first-stage regulator (2 psi) to the appliances and water heater: underground PE with tracer wire, regulators, shutoffs, gas solenoid valve and the encasement vent. Install LP conversion kits on the Owner's ranges; test, purge and obtain inspection.
· Fixtures (SK-1, SK-2, SK-3, FD-1, FS-1) with trim. WH-1 propane water heater with pad, venting and expansion tank; CP-1 circulator.
· Connections to dishwashers, ice maker and hoods; DOAS condensate to the existing catch basin, including exterior trench and restoration.
· Permits, coordination, access panels furnished, firestopping, as-builts and O&M.
· Include 10 CY of rock excavation per Section 220100.
· Alternates: Alt 3 – South wall sink and plumbing finish; Alt 7 – Demonstration station plumbing and gas finish.
References: Division 22. Drawings PD-101, P-001, P-101, P-401, P-402, A-911A. All other sections and sheets as they apply.
 
	3. WORK BY OTHERS AND CLARIFICATIONS



Not included: Removal and disposal of demolished plumbing (BP-01); Slab cutting (BP-01) and pour-back (BP-02); Propane tank and first-stage regulator (Owner/supplier); Power wiring (BP-12); Roof flashing (BP-09).
· The propane tank location is not shown. Price up to 175 LF developed length from the tank and state the length assumed.
· Alts 3 and 7: rough-in is in the Base Bid; the alternates are finish only.
 
	4. GENERAL REQUIREMENTS



· Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.
· Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.
· Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.
· School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).
· Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.
· Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

	BID FORM – BP-10 PLUMBING



The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-10 – Plumbing, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:
	Company
	
	NC License No. / Class
	

	Address
	
	Contact / Phone
	

	Email
	
	Prequalified? (Y/N)
	


A. Base Bid (lump sum, 100% turnkey)
	Written in words
	

	Figures
	$


B. Alternates (ADD or DEDUCT; write “No Change” if none)
	No.
	Description
	Amount

	Alt 3
	South wall sink and plumbing finish
	Add / Deduct $

	Alt 7
	Demonstration station plumbing and gas finish
	Add / Deduct $


C. Requested Pricing
	Description
	Amount

	Add for new propane tank and first-stage regulator through the gas supplier
	Add $


D. Unit Prices (installed, including overhead and profit)
	Description
	Unit
	Unit Price

	Underground 4" waste incl. excavation
	LF
	$

	1" propane piping
	LF
	$

	Additional floor drain
	EA
	$

	Rock excavation beyond 10 CY
	CY
	$

	Replace deteriorated existing cast-iron waste, 4"
	LF
	$


E. Lead Times and Duration
	Item
	Weeks / days
	Notes

	Submittals after award (working days)
	
	

	Material lead time (weeks)
	
	

	On-site duration (working days) / crew size
	
	


F. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)
	


G. Addenda Received
	No.
	
	No.
	
	No.
	
	No.
	


Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).
	Authorized Signature
	
	Date
	

	Name / Title
	
	Federal TIN
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