BID PACKAGE BP-11 – HVAC

Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425

Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)

Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525

1. SUMMARY AND KEY DATES

Make-safe for demolition, installation of the Owner-purchased DOAS, Type II kitchen hoods and exhaust fans, ductwork, controls, and TAB. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.

| Pre-bid meeting | Mon 10/12, 2:00 PM, Pender HS front office | Prequalification due | Wed 10/14, 5:00 PM |
| --- | --- | --- | --- |
| RFIs due | Wed 10/14, 5:00 PM, estimating@danddcc.com | Prequalified list / protests | Thu 10/15 / noon Fri 10/16 |
| Final addendum | Thu 10/15 | Bid opening | Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw |
| Notice to Proceed | 11/3/2026 (anticipated) | Substantial / Final | Jan 4 / Jan 15, 2027 (confirm by addendum) |

2. SCOPE OF WORK (furnish and install complete, including but not limited to)

- Coordinate HVAC demolition with BP-01: shut down, disconnect, cap and isolate systems per M-101, and mark items safe for removal. BP-01 removes and disposes. Isolate systems serving the work area from occupied areas. Recover any refrigerant from equipment being removed by EPA Section 608-certified technicians before BP-01 removal, with recovery records to the CM.

- Owner-purchased DOAS-1: coordinate delivery; receive, store, rig and set on the pad; ductwork through S1 with sleeve and seal; condensate trap; filters; start-up.

- Furnish and install Type II hoods H1–H4 per the Streivor 9/25/26 quote, hung from BP-13 supports.

- Exhaust fans F-4 (existing curb) and F-5 (new curb and deck cut), with grease-rated exhaust duct.

- Supply and transfer ductwork, dampers, air devices, insulation, and the duct smoke detector.

- DDC controls integrated into the existing TAC/CSI (Schneider) system by an authorized integrator: sequences, fan switches, hood auto-start and the gas solenoid interlock. All control wiring included.

- Independent TAB, including re-balancing PHP#2. Start-up, warranties, O&M and training.

- Relocate the existing thermostat and extend wiring; temporary filters at returns during construction and clean filters plus one spare set at turnover.

References: Division 23. Drawings M-001, M-101, M-102, M-701, QF-1, A-721. All other sections and sheets as they apply.

3. WORK BY OTHERS AND CLARIFICATIONS

Not included: Removal and disposal of demolished HVAC (BP-01); DOAS purchase (Owner); Equipment pad (BP-02); Support steel (BP-13); Power wiring and disconnects (BP-12, which governs over 230500); Roofing (BP-09); Condensate to catch basin (BP-10).

- The hood quote and drawings differ on size. Price four hoods per the Streivor quote models.

4. GENERAL REQUIREMENTS

- Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.

- Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.

- Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.

- School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).

- Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.

- Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

BID FORM – BP-11 HVAC

The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-11 – HVAC, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:

| Company |  | NC License No. / Class |  |
| --- | --- | --- | --- |
| Address |  | Contact / Phone |  |
| Email |  | Prequalified? (Y/N) |  |

A. Base Bid (lump sum, 100% turnkey)

| Written in words |  |
| --- | --- |
| Figures | $ |

B. Requested Pricing

| Description | Amount |
| --- | --- |
| Add to furnish DOAS-1 if not purchased by Owner | Add $ |
| Value of DOAS crane and rigging included in Base Bid | $ |

C. Unit Prices (installed, including overhead and profit)

| Description | Unit | Unit Price |
| --- | --- | --- |
| Additional insulated rectangular duct | LB | $ |
| Additional diffuser with flex runout | EA | $ |

D. Lead Times and Duration

| Item | Weeks / days | Notes |
| --- | --- | --- |
| Submittals after award (working days) |  |  |
| Material lead time (weeks) |  |  |
| On-site duration (working days) / crew size |  |  |

E. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)

F. Addenda Received

| No. |  | No. |  | No. |  | No. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).

| Authorized Signature |  | Date |  |
| --- | --- | --- | --- |
| Name / Title |  | Federal TIN |  |