BID PACKAGE BP-12 – ELECTRICAL, FIRE ALARM & LOW VOLTAGE

Scope of Work & Bid Form  |  Pender High School Food & Nutrition Lab Renovation  |  5380 NC-53 West, Burgaw, North Carolina 28425

Construction Manager at Risk: Daniels & Daniels Construction Co., Inc. | Owner: Pender County Schools | Architect: LS3P Associates Ltd. (7201-261295)

Bids due Tuesday, October 20, 2026, 2:00 PM  |  Questions: Erik Barrow, VP of Preconstruction, estimating@danddcc.com, 919-778-4525

1. SUMMARY AND KEY DATES

Make-safe for demolition, temporary power, new 300A DOAS service, Panel K, power, lighting, fire alarm, and low voltage. Bid per the ITB, the 95% Construction Documents dated September 29, 2026, and all addenda. Bidders must be prequalified.

| Pre-bid meeting | Mon 10/12, 2:00 PM, Pender HS front office | Prequalification due | Wed 10/14, 5:00 PM |
| --- | --- | --- | --- |
| RFIs due | Wed 10/14, 5:00 PM, estimating@danddcc.com | Prequalified list / protests | Thu 10/15 / noon Fri 10/16 |
| Final addendum | Thu 10/15 | Bid opening | Tue 10/20, 2:00 PM, Herring Resource Center, 798 US-117, Burgaw |
| Notice to Proceed | 11/3/2026 (anticipated) | Substantial / Final | Jan 4 / Jan 15, 2027 (confirm by addendum) |

2. SCOPE OF WORK (furnish and install complete, including but not limited to)

- Coordinate electrical demolition with BP-01: de-energize, disconnect and make safe all circuits per E-101, terminate back to source, and mark items safe for removal. BP-01 removes and disposes. BP-12 removes, stores and reinstalls the exit sign and fire alarm devices.

- Temporary power and lighting.

- New 300A service from the utility transformer to the fused DIS-DOAS, with grounding, plaques, trenching and restoration. Coordinate the utility tap and outage; utility charges are by the Owner.

- Panel K with feeder and breaker from existing 2MDP (field verify).

- All branch circuits, receptacles and island pop-ups (including underground conduit), and power wiring with disconnects and starters to all equipment, including DOAS, fans, hoods, WH-1, CP-1 and the gas solenoid.

- Lighting and controls per E-102.

- Fire alarm modifications including the duct detector and fan shutdown, programming and testing.

- TV and data outlets with Cat 6 cabling, WAP relocation, and boxes and raceway for Owner AV.

- Permits, labeling, testing, as-builts and firestopping.

- Fire alarm shop drawings, battery and voltage-drop calculations, and AHJ acceptance testing.

- Alternates: Alt 2 – West wall casework – devices; Alt 3 – South wall casework and sink – devices; Alt 7 – Demonstration station electrical finish.

References: Divisions 26 and 28. Drawings E-001, E-101, E-102. All other sections and sheets as they apply.

3. WORK BY OTHERS AND CLARIFICATIONS

Not included: Removal and disposal of demolished electrical (BP-01); Utility charges and AV equipment (Owner); Slab cutting (BP-01) and pour-back (BP-02); Controls and DDC wiring (BP-11).

- The feeder route is not dimensioned. Price 150 LF underground; the difference is adjusted by unit price.

- Alt 7: the Base Bid includes conduit only at the demonstration station; devices, wiring and connections are Alt 7.

4. GENERAL REQUIREMENTS

- Bid basis: Lump sum, complete and turnkey, including labor, material, equipment, supervision, hoisting, sales tax, permits and fees. This scope sheet assigns work between packages but does not limit it: work shown or specified that is customary to this trade is included.

- Bidding: Bid only on this Bid Form, in a sealed envelope marked with company name, bid package number and the bid opening location. Only exclusions written on the Bid Form are recognized. Bids are valid for 45 days.

- Insurance: WC statutory, EL $1M; CGL $1M/$2M; Auto $1M; Umbrella $1M. Owner and D&D named additional insured, with waiver of subrogation.

- School site: Background checks for all workers, ID worn, and no contact with students; E-Verify required. Noisy work and shutdowns are scheduled through the CM, and premium time is included. Hot work requires a permit and fire watch. Assume lead paint is present (RRP practices required).

- Each trade: Protects existing work and repairs its own damage, works within the dust partitions, cleans up daily, and uses the CM dumpster (BP-01 provides its own). Each trade also does its own layout, firestopping, and cutting and patching, except slab and GWB work assigned above.

- Schedule and closeout: Submittals are due within 10 working days of award. Man the job to the CM schedule, including winter break, and accept pass-through LDs of $500 per day. Provide as-builts, O&M manuals, warranties and training, with a one-year warranty from Substantial Completion.

BID FORM – BP-12 ELECTRICAL, FIRE ALARM & LOW VOLTAGE

The undersigned, having examined the site and the Bidding Documents, proposes to furnish all labor, materials, equipment and supervision for Bid Package BP-12 – Electrical, Fire Alarm & Low Voltage, Pender High School Food & Nutrition Lab Renovation, in accordance with the drawings, specifications and this scope sheet, for the following amounts:

| Company |  | NC License No. / Class |  |
| --- | --- | --- | --- |
| Address |  | Contact / Phone |  |
| Email |  | Prequalified? (Y/N) |  |

A. Base Bid (lump sum, 100% turnkey)

| Written in words |  |
| --- | --- |
| Figures | $ |

B. Alternates (ADD or DEDUCT; write “No Change” if none)

| No. | Description | Amount |
| --- | --- | --- |
| Alt 2 | West wall casework – devices | Add / Deduct $ |
| Alt 3 | South wall casework and sink – devices | Add / Deduct $ |
| Alt 7 | Demonstration station electrical finish | Add / Deduct $ |

C. Requested Pricing

| Description | Amount |
| --- | --- |
| Deduct if DOAS is fed from existing 2MDP in lieu of new service | Deduct $ |

D. Unit Prices (installed, including overhead and profit)

| Description | Unit | Unit Price |
| --- | --- | --- |
| 300A feeder, underground incl. trench | LF | $ |
| Additional 20A receptacle circuit | EA | $ |
| Additional data drop, Cat 6 | EA | $ |

E. Lead Times and Duration

| Item | Weeks / days | Notes |
| --- | --- | --- |
| Submittals after award (working days) |  |  |
| Material lead time (weeks) |  |  |
| On-site duration (working days) / crew size |  |  |

F. Bidder’s Exclusions and Qualifications (only items listed here will be recognized)

G. Addenda Received

| No. |  | No. |  | No. |  | No. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Certification: Bidder accepts the Invitation to Bid and this scope sheet; will honor this bid for 45 days; will comply with the Owner’s background checks, E-Verify and the insurance requirements; and represents that this bid was prepared without collusion (Sherman Act and NC law).

| Authorized Signature |  | Date |  |
| --- | --- | --- | --- |
| Name / Title |  | Federal TIN |  |