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INVITATION TO BID
Pender High School Food & Nutrition Lab Renovation
5380 NC-53 West, Burgaw, North Carolina 28425

Daniels & Daniels Construction Co., Inc., Construction Manager at Risk for Pender County Schools, invites sealed lump-sum bids from first-tier subcontractors for the bid packages listed below. The project consists of the renovation of approximately 1,586 square feet of existing instructional space into a food and nutrition lab within an occupied school.

Project Team
· Owner: Pender County Schools
· Architect: LS3P Associates Ltd., Wilmington, NC (Commission No. 7201-261295)
· Engineers: Woods Engineering (Structural); Cheatham & Associates, P.A. (Plumbing, Mechanical, Electrical)
· Construction Manager at Risk: Daniels & Daniels Construction Co., Inc.

Key Dates
· Pre-Bid Meeting: Monday, October 12, 2026 at 2:00 PM – Pender High School, 5380 NC-53 West, Burgaw, NC. Attendance is strongly recommended but not mandatory. All visitors must check in at the school front office.
· Prequalification Forms Due: Wednesday, October 14, 2026 by 5:00 PM, by email to estimating@danddcc.com or hand delivery to the Daniels & Daniels office, 178 NC-111 Hwy S, Goldsboro, NC. Prequalified bidder list and denial notices issued Thursday, October 15; protests due in writing by 12:00 noon Friday, October 16 and decided by end of that day.
· Questions / RFIs Due: Wednesday, October 14, 2026 by 5:00 PM, in writing to the CM contact below
· Final Addendum Issued: Thursday, October 15, 2026
· Bid Opening: Tuesday, October 20, 2026 at 2:00 PM – Pender County Schools, Dr. Katherine Herring Resource Center, 798 US-117, Burgaw, NC 28425. Bids will be opened publicly. Late bids will not be accepted.
· Anticipated Notice to Proceed: November 3, 2026

Bid Packages
	Package
	Scope of Work

	BP-01
	Selective Demolition – interior demolition per AD-101A, VCT and mastic removal, CMU and stud wall removal, casework and fixture removal, slab sawcut and removal for underground utilities (Section 024100)

	BP-02
	Concrete – slab pour-back at utility trenches (S2), DOAS equipment pad, new concrete walkway

	BP-03
	Masonry – exterior brick/CMU patching at removed exhaust and dryer vents, masonry repair at new openings

	BP-04
	Aluminum Storefront & Glazing – Storefront S2 with pair of entrance doors (100A) and hardware, Storefront S1 panel bay with Mapes panels (Sections 084313, 087100, 088000)

	BP-05
	Metal Studs, Drywall & Acoustical Ceilings – partitions, furring, soffits, blocking, ACT-1 ceilings (Sections 061053, 092116, 095100)

	BP-06
	Architectural Casework & Countertops – PLAM island casework, spine wall panels, countertops; Alternates 2, 3, 5, 6 and 7 (Sections 062000, 064100, 123600)

	BP-07
	Flooring – substrate preparation, sealed concrete with slip-resistant finish, resilient base; Alternate 4 resinous flooring (Sections 090561, 099123)

	BP-08
	Painting & Wall Graphics – interior painting; Alternate 1 experiential graphics (Sections 097200, 099123)

	BP-09
	Roofing – roof patching and flashing at new exhaust fan curbs

	BP-10
	Plumbing – underground and above-grade waste/vent, domestic water, propane gas piping and regulators, fixtures, water heater WH-1, condensate drain (Division 22)

	BP-11
	HVAC – install Owner-furnished DOAS-1, exhaust fans, ductwork, Type II kitchen hoods H1–H4 (furnish & install), controls, test & balance (Division 23)

	BP-12
	Electrical, Fire Alarm & Low Voltage – new 300A service and DOAS disconnect, Panel K, branch power, lighting, fire alarm modifications, data/TV outlets (Divisions 26, 28)

	BP-13
	Miscellaneous Metals (Division 5) – kitchen hood support framing, roof opening framing at exhaust fans, miscellaneous steel (Section 055000)

	BP-14
	Specialties (Division 10) – semi-recessed fire extinguisher cabinet and extinguisher, 12-hook system HK1, room and code signage (Section 104400)



Alternates
Bidders shall price every Add Alternate that applies to their package as a separate add amount on the bid form, as described in Section 012300:
	Alternate
	Description

	Alt 1
	Experiential graphics, including design

	Alt 2
	Casework along west exterior wall

	Alt 3
	Casework and sink along south interior wall

	Alt 4
	Resinous (epoxy) flooring EPF-1

	Alt 5
	Porcelain countertops

	Alt 6
	Floating wood shelves

	Alt 7
	Demonstration station



Bidding Documents
95% Construction Documents (35 sheets) and Project Manual dated September 29, 2026, prepared by LS3P. Documents are available on the Daniels & Daniels website at www.danddcc.com. Bidders are responsible for reviewing all drawings and specifications, not only those for their trade, and for acknowledging all addenda on the bid form.

Bid Requirements
· Lump-sum base bid per package, with each applicable alternate listed separately, on the CM-provided bid form.
· Prequalification is required of all first-tier subcontractors per G.S. 143-128.1. The Subcontractor Prequalification Form is available at www.danddcc.com. Bids will be accepted only from prequalified firms.
· Include all applicable North Carolina sales tax. Comply with the E-Verify requirements of G.S. 143-133.3.
· Bids remain valid for 45 days after bid opening.

Instructions to Bidders
· Bids must be submitted on the bid form provided by Daniels & Daniels. Bids not on the provided form will not be accepted.
· Bids must be submitted in a sealed envelope. The outside of the envelope must show the bidder’s company name, the bid package number(s), and the bid opening location: Pender County Schools, Dr. Katherine Herring Resource Center, 798 US-117, Burgaw, NC 28425.
· Sealed bids must be received at the bid opening location before 2:00 PM on Tuesday, October 20, 2026.

Owner-Furnished Items
The following are furnished by the Owner and installed and/or connected by the Contractor: DOAS-1 dedicated outdoor air unit; dishwashers DW1 and DW2; ranges RE1 and RE2; refrigerators REF1; freezer FZ1; ice maker ICE1; 55" TV monitors; existing lockers (relocated). Paper towel and soap dispensers are furnished and installed by the Owner.

Site Conditions
· Work is within an occupied school. Coordinate all activities with Pender County Schools to maintain campus operations.
· On-site work hours are 7:00 AM to 7:00 PM, Monday through Friday, unless otherwise approved.
· All personnel must complete Owner-required criminal background and sex offender registry checks and wear identification at all times.
· Tobacco, alcohol, and controlled substances are prohibited on school property.

Small Business Participation
Daniels & Daniels encourages participation by small businesses and will make a good faith effort to recruit and select small business entities in accordance with G.S. 143-128.1. Historically Underutilized Business (HUB) forms in the Project Manual are no longer required following the repeal of G.S. 143-128.2 by S.L. 2026-41 and will be addressed by addendum.

Pender County Schools and Daniels & Daniels Construction Co., Inc. reserve the right to reject any or all bids and to waive informalities.

Construction Manager Contact
Erik Barrow, Vice President of Preconstruction
Daniels & Daniels Construction Co., Inc.
Phone: 919-778-4525  |  Email: estimating@danddcc.com
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